## Risk Register
AI Risk Register — NIST AI RMF Sample
Portfolio piece · mapped to NIST AI RMF: Govern, Map, Measure, Manage
ID | NIST Function | AI System | Risk Description | Likelihood | Impact | Rating | Mitigation / Control | Owner
GRC-001 | Govern | Customer support chatbot | No documented owner for model updates; changes ship to production without GRC review. | Medium | High | High | Require GRC sign-off in the change-control process before any model update ships. | Head of AI Governance
GRC-002 | Govern | Enterprise-wide | No approved AI acceptable-use policy — employees use unsanctioned AI tools with company data ("shadow AI"). | High | High | Critical | Publish an AI acceptable-use policy; train staff; maintain an approved-tools list. | CISO / GRC Lead
GRC-003 | Map | Resume-screening model | Use case and risk tier undocumented; unclear if it qualifies as "high-risk" under emerging AI regulation. | Medium | High | High | Complete an AI system inventory and risk-tiering exercise against EU AI Act / NIST categories. | AI Governance Analyst
GRC-004 | Map | Marketing content generator | Third-party model provider's data handling and training-data provenance not reviewed. | Medium | Medium | Medium | Require a vendor AI risk questionnaire and signed data processing agreement before use. | Procurement / GRC
GRC-005 | Measure | Resume-screening model | No bias/fairness testing performed against protected classes since last retrain. | High | High | Critical | Implement quarterly bias audits with documented disparate-impact testing. | Data Science + GRC
GRC-006 | Measure | Customer support chatbot | No monitoring for hallucinated or incorrect responses in production. | High | Medium | High | Stand up a response-accuracy sampling process with monthly review. | AI Product Owner
GRC-007 | Manage | Enterprise-wide | No incident response plan covers AI-specific failures (e.g., biased output made public). | Low | High | High | Extend the incident response plan to cover AI-specific triggers and escalation paths. | CISO
GRC-008 | Manage | Resume-screening model | Remediation plan for flagged bias findings has no defined timeline or re-test requirement. | Medium | High | High | Define an SLA for remediation and require re-testing before re-deployment. | AI Governance Analyst

## Summary
Risk Register — Summary
By Rating
Rating | Count
Critical | 2
High | 5
Medium | 1
Low | 0
Total | 8
By NIST Function
Function | Count
Govern | 2
Map | 2
Measure | 2
Manage | 2
Total | 8